## Sheet1
Impact
|  | 1 | 2 | 3 | 4 | 5
Probability | 1 | [5 empty] | Key |  | Edited/added after initail completion of risk assesment
| 2 | [6 empty] | Extremley Low
| 3 | [6 empty] | Low
| 4 | [6 empty] | Moderate
| 5 | [6 empty] | High

## Sheet2
No. | Risk | Effect | Cause | Likelihood | Impact | Matrix | Soloution
1 | Over reaching on the project | Overreaching on the project will lead to the project becoming too complicated . This in turn will mean that I might not be able to turn in a finished product and I might lose motivation for the project. | Overestimation of my abilities. | 2 | 4 |  | Keep the project simple while still meeting all then targets and if I have extra time at the end of the project I can then slowly add extra features once the core project is done.
2 | Project not meeting the specifications | Not meeting the specifications will lead to a project that isn't complete and will then mean a bad mark for the SFIA project. | Not understanding the specification. | 1 | 3 |  | Talk to others doing the project and also those who set the specification to make sure my project meets the specification.
3 | Organising the tasks ineffectively | Non efficient organisation of the tasks will lead to tasks taking longer the necessary and could impact the overall time needed for the task and possibly cause me not to make the deadline. | Planning to do tasks before I'm capable, planning to do tasks before their respective prerequisite tasks aren't complete | 2 | 3 |  | Plan when I'm doing specific tasks to coincide with when I have completed the training and also setting tasks to be complted in the correct order so any prerequisite tasks are complete first.
4 | Change of project specification | A change of project specification will lead to me having to possibly revise my project idea and structure if it doesn't meet the new specifications. The later the change in specification happens then larger the impact will be. | Change of project specification | 2 | 3 |  | Make sure that I allow extra time in my plan for any changes and also make sure that I'm always ahead/on schedule so that I have time to adapt to any change in product specification
5 | Falling ill | Falling ill will affect the amount of time I can put into the project causing me to possibly fall behind my schedule as well as effect the quality of any work that I might produce during that time | Stress, poor personal hygiene, poor diet | 4 | 4 |  | Follow basic hygiene routines as well as making sure I have regular healthy meals. Allow for time in my schedule to catch up on any work that I have fallen behind on
6 | Eye strain | The effects of eye strain is tired or sore, burning and/or itchy feeling in the eye area. Difficulty focusing, increased sensitivity to light, blurred or double vision and other sensations of eye discomfort accompanied by headaches. | Looking at a computer screen for long periods of time | 2 | 1 |  | Follow the 20-20-20 rule, for every 20 minutes looking at a screen take 20 seconds to view something 20 feet away
7 | Various long term health problems caused by sitting for long periods of time | sitting for long periods every day could cause many various health problems, including Varicose veins, increase in weight and deep vein thrombosis to name a few. | sitting for long periods of time | 2 | 2 |  | take regular breaks to get up and walk around briefly
8 | Coronavirus | Global pandemic that could possibly lead to lockdowns, curfews and inability to travel | Coronavirus | 5 | 2 |  | Follow governments advice on dealing with Coronavirus and be prepared to remote work from home making sure I have all the necessary equipment and tools to remote learn
9 | SQL Database is compromised | Loss of some tables within database or complete loss of all data and complete destruction of entire database | Weak passwords, bad security or malicious attack | 3 | 2 |  | Use a secure password and have correct security protocols in place. Also have SQL code prewritten ready to recreate and refill database if needed.
10 | Virtual machine instances are compromised | Loss of application functionality | Weak passwords, bad security or malicious attack | 2 | 4 |  | Be prepared to possibly set up new virtual machines if necessary and destroy the old ones
11 | Jenkins is compromised | Loss of app functionality and loss of CI | Weak passwords, bad security or malicious attack | 2 | 4 |  | Be prepared to set up a new Jenkins environment and pipeline for my application
12 | My Dockerhub is compromised | Loss of application functionality | Weak passwords, bad security or malicious attack | 2 | 4 |  | Be prepared to set up a new docker account and host all images locally as well as on docker hub
13 | GCP is overworked | SQL functions may be delayed, Virtual machines may be delayed | Too many users accessing the site due to the increase in people working from home | 4 | 2 |  | Be patient and work on other parts of the project so time isnt wasted. Also have a prerecorded demo of the application incase this happens during my presentation.